## Slide 1
ENDLESS
Phase 1 — Phantom Layer MVP
How it gets built. Sandboxed execution, verified callers, gap clustering, mass scoring, creator onboarding and a public gaps board.
Done when a creator publishes a tool, an agent finds and calls it, and repeated gaps surface automatically.

## Slide 2
ABOUT THIS PHASE
What Phase 1 is for
Read this first if you have not read PROJECT.md.
Endless, in one sentence. A shared registry of small tools that AI agents search through — and every search that finds nothing is recorded, so the list of missing tools comes from real use rather than guesswork.
Phase 0 built the searching and the recording. It finds the right tool, and it knows when none fits. But nothing has ever been run, nobody outside this project has used it, and no gap on the list came from a real need.
Phase 1 is where Endless stops being a catalogue that DESCRIBES tools and becomes a platform that RUNS them.
Three things become real. An agent can call a tool and get a result. Someone who is not you can publish one. The gaps list becomes a public page.
Which makes it the riskiest phase so far. Each opens a door that was closed: running code you did not write, trusting submissions from strangers, and publishing something people have a reason to manipulate.
So most of Phase 1 is containment, not features. The sandbox, verified identity and the review gate are all there because of those three doors.

## Slide 3
STARTING POINT
What Phase 0 leaves behind
Working machinery, no users, and two findings that change how Phase 1 is built.
Already built | State
Registry with immutable versions | live, proven by test
Semantic search, hybrid dense + BM25 | recall@3 100% on two sets
Gap detection via an LLM adjudicator | 96.7% detection, 6.7% false
Append-only event log | IAM-enforced, replayable
Terraform + OIDC CI/CD | full rebuild from zero, three times
19 seeded tools, 120 frozen eval queries | committed, checksummed
Two findings Phase 1 inherits. An adjudicating LLM is not optional — without it the gap log runs at 20% false positives. And descriptions must never say what a tool is NOT: negation makes retrieval worse, measurably.
One thing Phase 0 could not do. Prove anyone wants the missing tools. Every gap ever logged came from the test harness.

## Slide 4
SCOPE
What Phase 1 adds, and what it does not
Phase 1 delivers | Still deferred
Sandboxed execution of third-party code | Tool-to-tool calls — Phase 2
Caller identity, so provenance is real | Brightness, decay, dependency weight — Phase 2
Real MCP endpoints agents can call | Agents building their own tools — Phase 3
Gap clustering, so demand repeats visibly | Applications joining from outside — Phase 4
Mass-only scoring from the event log | Galaxies and routing mini-LLMs — Phase 5
Creator onboarding behind a review gate | The 3D visual layer — Phase 6
A public gaps board | Money of any kind — Phase 8
Mass-only is deliberate. Brightness needs call outcomes at volume, and Phase 1 is the phase that first produces them. Scoring on one signal is honest; scoring on two when one has no data is not.

## Slide 5
ARCHITECTURE
What runs in Phase 1
Green is new. The full diagram is on the Miro board beneath Phase 0.
CALLERS
Agent
calls tools
Creator
publishes tools
EDGE
auth-fn
verifies the API key
NEW
CONTROL PLANE
search-fn
rank + adjudicate
exec-fn
call a tool
NEW
submit / review
the review gate
NEW
SANDBOX
tool-runtime
no network, null role
NEW
fetcher-fn
the only thing online
NEW
7 tables
3 existing, 4 new
EventBridge
nightly jobs
NEW
cluster + score
replay the log
NEW
gaps board
CloudFront + S3
NEW
Bedrock
embed + adjudicate

## Slide 6
THE KEY DECISION
The sandbox, and why it is shaped this way
This is the hardest thing in Phase 1 and the one worth getting right first.
A tool never opens a network connection. It declares the endpoint it needs. The platform fetches that endpoint against a per-tool allowlist and hands back the response. The tool only transforms data.
So the sandbox has nothing to contain. No network, no IAM role, no disk. An escape reaches an empty room — there is no credential to steal and nowhere to send it.
The alternative was containing arbitrary code WITH internet access. That is an open-ended problem. Egress filtering, DNS rebinding, exfiltration through a permitted host. This design removes the category instead of defending it.
The cost is real and should be stated up front: a tool needing several chained calls, or an endpoint not known until runtime, does not fit. That limit is the price of a sandbox whose safety can actually be argued about rather than hoped for.
Two ways to run it: Fargate tasks, or Lambda in a VPC with no NAT gateway. Both give no egress; the Lambda route stays inside the free tier.

## Slide 7
SECOND DECISION
Caller identity — an invariant that is currently broken
THE HOLE
// today, search-fn trusts what the caller claims about itself
{ "query": "...", "actor": { "agent_id": "anything-i-like",
"session_id": "also-anything" } }
CLAUDE.md invariant #4. A gap record must carry which agent and session produced it, "so manufactured demand can be traced".
It cannot be traced today. The actor is self-asserted in the request body. Anyone can log a thousand gaps as a thousand different agents and manufacture a trend on the gaps board.
This did not matter in Phase 0. The only caller was the eval harness. It matters the moment the gaps board is public and there is a reason to game it.
The fix. Hashed API keys per caller, verified at the edge. Events record the verified caller id and ignore anything the body claims. Gap clustering then counts DISTINCT VERIFIED callers, which is what makes a cluster evidence.

## Slide 8
THIRD DECISION
Gap clustering — making "repeated" mean something
The Done-when says repeated gaps surface automatically. Repetition needs defining.
Cluster by meaning, not by string. "will it rain tomorrow" and "what is the forecast for Friday" are the same unmet need. Embeddings already exist for this.
Count distinct callers, not occurrences. One agent in a retry loop is not demand. Ten callers asking the same thing once each is. This is the entire reason caller identity has to land first.
Run it nightly, off the hot path. EventBridge triggers a job that reads the gap log and writes clusters. Nothing about search gets slower.
Surface a cluster when distinct callers cross a threshold. That threshold is a Phase 1 output, derived from the data, not a number picked now — the same discipline that Phase 0 applied to T, and for the same reason.
A cluster of one caller is a curiosity. A cluster of twelve is a product brief. The gaps board only means anything if that distinction is enforced.

## Slide 9
PLAN
Thirteen issues
Estimates for one developer.
# | Issue | Est. | Depends on
1 | Caller identity: hashed API keys, verified at the edge | M | -
2 | Tool package format, S3 upload, bound to a version | M | -
3 | Sandbox runtime: no network, null role, no disk | L | 2
4 | Platform fetcher with a per-tool allowlist | M | 3
5 | Sandbox escape tests | M | 3, 4
6 | exec-fn: call a tool, record the outcome event | M | 1, 4
7 | MCP endpoints so agents can actually call tools | M | 6
8 | Gap clustering job, nightly | M | 1
9 | Repeated-gap rule: distinct-caller threshold, derived | S | 8
10 | Mass-only scoring, recomputed from the event log | M | 6
11 | Creator submission API and review gate | M | 1, 2
12 | Public gaps board: CloudFront, S3, read-only API | L | 9
13 | Phase 1 findings write-up | S | all

## Slide 10
SEQUENCING
What blocks what
#1 Identity
#2 Package
#3 Sandbox
#4 Fetcher
#5 Escape tests
#6 exec-fn
#5 is a gate, not a task. No third-party code runs until the escape tests pass. CLAUDE.md is explicit that sandboxing is not a later phase — it gates everything.
#1 comes first because two things depend on it. Clustering counts distinct verified callers, and the review gate needs to know who submitted. Retro-fitting identity after the gap log has data means the early data cannot be trusted.
#12 is the cold-start move, and it can start early. PROJECT.md calls the gaps board a standalone product useful before the ecosystem exists. It only needs #9, so it can run in parallel with the sandbox work.
#13 is the exit, as in Phase 0. The gate clears, or a written finding says why not.

## Slide 11
COST
What Phase 1 costs to run
Phase 0 cost under $5. Phase 1 breaks the always-free pattern in two places.
Component | Free tier | Phase 1 reality
Lambda, DynamoDB, EventBridge | always free within limits | still free at this volume
Bedrock: embeddings + adjudicator | none | per search, grows with traffic
Sandbox on Fargate | none | per task-second — the main new cost
Sandbox on Lambda in a VPC | always free | free, slightly weaker isolation
CloudFront + S3 for the board | 1 TB out free for 12 months | free at any plausible volume
The honest number is unknown until #6. Cost per call depends on how long tools run, and nothing has ever executed. Measure it in #6 and publish it with the findings.
PROJECT.md already made this a standing commitment. "Measure per-call cost continuously — compute, embeddings and routing all sit on the path of every call."
Decide the runtime on cost, not instinct. Lambda-in-a-VPC is free and gives the same no-egress guarantee. Fargate is stronger isolation and costs per second. Both are defensible; drifting into Fargate without deciding is not.

## Slide 12
RISKS
What could go wrong, and what was already logged
The sandbox is the whole phase. If it slips, everything after #6 slips with it. It is also the one item with no Phase 0 precedent — nothing has ever been executed.
Clustering can manufacture demand. Without verified identity, or with a threshold set too low, the gaps board shows trends that nobody asked for. That would discredit the product more thoroughly than shipping nothing.
Mass rewards whoever arrives first. Already filed against Phase 4 in docs/deferred-corrections.md: expedited review buys ranking indirectly, because mass accumulates over time. Worth resolving before mass means money.
The eval set must grow with the corpus. Also filed. 120 queries against 19 tools is thin already; against 200 it measures almost nothing.
Still no users. Phase 1's Done-when begins "a creator publishes a tool" — a person who is not you. Phase 0 ended with working machinery and nobody using it. Phase 1 will too, unless recruiting the first creator is scheduled as work.

## Slide 13
THE GATE
What would prove Phase 1, and what would falsify it
Must be true | How it is checked
A creator who is not you publishes a tool | the submission passes the review gate and appears in the registry
An agent finds it and calls it | a call event exists with a verified caller id and a real outcome
Untrusted code cannot reach anything | escape tests pass: no network, no IAM, no disk
Repeated gaps surface on their own | a cluster crosses the distinct-caller threshold with no manual step
Mass is recomputable | scores rebuilt from the event log alone match the stored ones
False-gap rate stays bounded | re-run both eval sets; the Phase 0 ceiling still holds
Add the false-gap ceiling to this gate explicitly. Phase 0's gate passed while a third of answerable queries were being logged as unmet needs, because it never asked that question. Do not repeat a test with a hole the size of the product's core claim.

## Slide 14
START HERE
The first five moves
1
Decide the sandbox runtime — Fargate or Lambda in a VPC — on cost, before writing it
2
Build caller identity first; everything that counts demand depends on it
3
Write the sandbox escape tests before the sandbox, so they cannot be shaped to pass
4
Start the gaps board early — it is the only item that gives an outsider a reason to arrive
5
Find one creator who is not you, and treat that as work in the phase, not a hope at the end
Architecture: miro.com/app/board/uXjVHpGFCos= · Phase 0 findings: docs/phase-0-findings.md