## Slide 1
ENDLESS
Phase 0 — Validate the Loop
The smallest system that can tell a real unsolved need from a search failure — how the plan works, how the board works, and how it gets built on AWS.
Endlessandothers/Endlessproject · 8 September 2026 · 12 issues · about 6 weeks · under $2

## Slide 2
CONTEXT
What Endless is
A shared universe of small tools that AI agents discover and call.
The inversion. Most tool marketplaces are static directories: you publish and hope. Endless logs every agent search that finds nothing, so normal usage generates demand signal for free. Creators stop guessing what to build and read what agents repeatedly failed to find.
Phantom layer. The machine substrate — registry, semantic search, gap logging, gravity scoring, routing, sandboxed execution. Ranking here is earned through usage and cannot be purchased.
Visual layer. A navigable 3D world where tools render as celestial bodies sized by their real standing. Sponsorship and paid placement live here only, and it never writes ranking back.
Money buys what humans see. Merit decides what agents use. Collapsing the two would destroy the reason an agent can be trusted to pick well.

## Slide 3
PURPOSE
Phase 0 exists to answer one question
Is a logged gap real evidence of an unsolved need, or just a search failure?
Why it decides everything. The whole pitch is that gap logs are a usage-verified map of real unsolved problems. If the signal is noisy, creators get a roadmap of nothing and the value proposition collapses.
PROJECT.md already flags it. Telling 'no tool exists' from 'the agent searched badly' is named as genuinely unsolved. Search quality must be strong before gap logging means anything.
So the gate is measured, not asserted. No gap counts as evidence until a labelled eval set shows recall@3 of at least 0.9.

## Slide 4
SCOPE
What is in Phase 0, and what is deliberately not
In scope | Out of scope — and why
Tool registry with immutable versions | Sandboxed execution — Phase 0 never runs a tool
Semantic search over registered tools | Gravity scoring, mass and brightness — Phase 2
Append-only, provenance-tagged event log | Mini LLMs, heartbeats, routing — Phase 3
Gap detection and gap log | The 3D visual layer — Phase 4
15-20 seeded tools wrapping public APIs | Billing, payouts, sponsorship — Phase 6
Labelled eval set and recall@k harness | Any user interface — CLI only for now
PROJECT.md names scope as the biggest risk: the full vision is five products at once. Phases 0-2 need no 3D and no LLM routing, which is why this plan stops hard at the edge of Phase 0.

## Slide 5
PART ONE
The Miro board
One canvas, three regions: the architecture, the schedule and the dependency graph. How to read and edit each.

## Slide 6
THE BOARD
How the board is laid out
miro.com/app/board/uXjVHpGFCos=
Region | What it is | How you edit it
Architecture frame | A titled Miro frame, 2000 x 1350 px | Drag boxes; the frame moves them together
Timeline | A native Miro timeline widget, not a picture | Drag bars to reschedule; edit cells
Dependency graph | A diagram widget generated from Mermaid | Edit the source and regenerate
Everything sits on one infinite canvas. There is no slide order. The architecture is at the top; the schedule and dependency graph sit below it, side by side.
The frame is the unit that matters. Anything inside the architecture frame has coordinates relative to the frame's top-left corner, so moving the frame moves the whole diagram intact.
Any widget can be deep-linked. Append ?moveToWidget=<id> to the board URL and opening it pans straight to that widget — useful for pointing a collaborator at one specific box.

## Slide 7
THE BOARD
Reading the architecture frame
Icons are real AWS assets. Each service carries its official icon as a badge on its top-left corner, taken from AWS Labs' own icon repository — not an approximation.
Dashed rectangles are zones. They group services by AWS category and carry the free-tier limit in the label, so the constraint is visible where the decision gets made.
Fill colour encodes layer. Amber is compute, blue is storage, green is the one paid component, grey is supporting.
Connector labels are the contract. Each arrow says what crosses it — 'write new version', 'log gap below threshold T' — rather than just pointing.
registry-fn
tool CRUD, immutable versions
search-fn
embed, cosine rank, gap check
events
append-only, provenance-tagged
Bedrock
Titan Embeddings V2 — only paid
The badge convention used on the board

## Slide 8
THE BOARD
The timeline is a live widget, not a picture
It is a Miro table in timeline layout. The same twelve issues are rows. Switch the widget to table or kanban and it is the same data in a different shape.
Columns carry meaning, not just text. Start Date and End Date drive the bars, Status drives colour, Priority marks the critical path. Those names are fixed — the widget binds to them by name.
Drag a bar and the data changes. Rescheduling on the canvas edits the underlying dates. It is the schedule, not a rendering of one.
Which means it will drift from the repo. The plan document holds a Mermaid Gantt with the same dates. Pick one as authoritative — I suggest the board for dates, the repo for scope.
Column | Type | What it drives
Title | text | The bar label
Start Date / End Date | date | Bar position and length
Status | select | Bar colour: Todo, In progress, Done
Priority | select | Critical path versus Normal
Estimate | number | Days of effort

## Slide 9
THE BOARD
The dependency graph is generated, not drawn
It is a diagram widget backed by Mermaid source. The board stores the Mermaid text, so the graph is edited as code rather than by dragging boxes around.
Green is the critical path. #1, #3, #4, #6, #10, #12 — the chain that sets the length of the phase.
Editing means editing the source. Hand-moving nodes fights the renderer. Change the Mermaid and regenerate.
THE SOURCE BEHIND THE GRAPH (ABRIDGED)
flowchart TD
classDef crit fill:#adf0c7,stroke:#087429
I1[#1 Scaffold] --> I3[#3 CDK] --> I4[#4 Registry]
I4 --> I6[#6 Search] --> I10[#10 Eval] --> I12[#12 Findings]
I4 --> I9[#9 Seed tools] --> I10
class I1,I3,I4,I6,I10,I12 crit

## Slide 10
PART TWO
The architecture
What runs, what it costs, and which decisions were deliberate.

## Slide 11
ARCHITECTURE
AWS free-tier architecture
Every box sits inside an always-free monthly limit, except the green one.
Agent / CLI
the caller
COMPUTE — LAMBDA FUNCTION URLS
registry-fn
tool CRUD, immutable versions
search-fn
embed, cosine rank, gap check
events-fn
append-only writer
STORAGE — DYNAMODB (PROVISIONED)
tools
PK tool_id / SK version
events
append-only, provenance
gaps
append-only, provenance
Bedrock
Titan Embed V2
ONLY PAID COMPONENT
S3
vector snapshots, warm start
CloudWatch
logs and the $5 billing alarm

## Slide 12
ARCHITECTURE
The request path, step by step
1
Caller asks. An agent or the CLI posts a natural-language query to the search-fn Lambda Function URL.
2
Query is embedded. search-fn calls Bedrock Titan Embeddings V2 and gets a 1024-dimension vector. The only call that costs money.
3
Ranking happens in memory. Tool vectors were loaded at cold start and cached in module scope. Cosine over ~20 vectors is sub-millisecond.
4
An event is written, always. Success or failure, an event carrying agent id and session id is appended before the response returns.
5
A gap is logged, conditionally. If the top score is below threshold T, or the caller rejects every result, a gap is appended with the full top-k and the value of T in force.
6
A human reads the log. The phase ends with you judging gaps by hand. That is the deliverable: evidence, not infrastructure.

## Slide 13
ARCHITECTURE
How the architecture enforces the invariants
CLAUDE.md lists five non-negotiables. Three are live in Phase 0.
Invariant | How Phase 0 enforces it
Gap logs append-only and provenance-tagged | IAM grants PutItem and Query, never UpdateItem or DeleteItem
Tool versions immutable once published | Re-registering writes a new sort key; a test proves no mutation
Scoring recomputable from the event log | Every search emits an event; a test replays the log to recompute
All third-party code runs sandboxed | Not yet triggered — Phase 0 never executes a registered tool
Money never affects agent-facing ranking | Not yet triggered — no money, no ranking, no visual layer
The last two are scope decisions, not oversights. The moment execution arrives in Phase 1, mandatory sandboxing gates everything.

## Slide 14
KEY DECISION
The deliberate non-decision: no vector database
Phase 0 has 15-20 tools. Cosine similarity over 20 vectors in Lambda memory is sub-millisecond and costs nothing.
A vector store answers none of the phase's questions. OpenSearch or pgvector for 20 rows spends the phase on infrastructure instead of evidence — and OpenSearch is not always-free.
The interface is what matters. Search sits behind an interface with a single implementation, swappable in Phase 1 without touching callers.
Choose it later, with data. The Phase 1 store gets picked from real Phase 0 query distributions rather than guessed at now.
Same reasoning picked Lambda Function URLs over API Gateway: Lambda and DynamoDB have always-free allowances, API Gateway is free for 12 months only. Given the free-tier change, that distinction matters.

## Slide 15
PART THREE
Building Phase 0 on AWS
Nine steps from an empty account to a running loop, in the order they have to happen.

## Slide 16
BUILD · STEP 1
Account, region and guardrails
Do this before writing a line of code.
1
Pick one region and stay in it. Bedrock model availability varies by region. us-east-1 has the widest coverage. Mixing regions is the most common way this stalls.
2
Never build on the root user. Create an IAM Identity Center user with admin rights and MFA, and use that.
3
Set the billing alarm first, not last. A CloudWatch billing alarm at $5. Billing metrics only publish in us-east-1, so create the alarm there even if you build elsewhere.
4
Know which free tier you are on. Accounts opened since 9 July 2025 get credits over 6 months and then close. Older accounts get the legacy 12-month tier.

## Slide 17
BUILD · STEP 2
Enable Bedrock model access
Bedrock models are off by default. This is a manual console step.
Console path. Bedrock, then Model access, then request Amazon Titan Text Embeddings V2. Approval is usually immediate but never automatic. Then verify from the CLI before trusting it.
CONFIRM THE MODEL IS AVAILABLE TO YOU
$ aws bedrock list-foundation-models --region us-east-1 \
--by-provider amazon \
--query "modelSummaries[?contains(modelId,'titan-embed')].modelId"
[ "amazon.titan-embed-text-v2:0" ]
Property | Value
Model ID | amazon.titan-embed-text-v2:0
Output dimensions | 1024 default; 512 and 256 also supported
Max input | 8,192 tokens / 50,000 characters
Throttling | by requests per minute, not tokens per minute

## Slide 18
BUILD · STEP 3
Repo and toolchain
TARGET LAYOUT (ISSUE #1)
Endlessproject/
services/
registry/ tool CRUD
search/ embed + rank + gap
events/ append-only writer
packages/
schemas/ Tool, Event, Gap
infra/ CDK app
docs/
PROJECT.md
plans/
Node 20 with npm workspaces. One toolchain now, and the same one later for the console and the 3D world.
Two housekeeping fixes belong here. Rename CLAUDE (5).md to CLAUDE.md so its invariants actually load, and move PROJECT.md into /docs to match the documented layout.
Only Phase 0 directories exist. gravity, routing, sandbox, billing and apps stay absent until their phase. An empty directory is a promise you have not kept.

## Slide 19
BUILD · STEP 4
The CDK stack
One stack creates everything; a clean clone deploys in one command.
ONE-TIME SETUP, THEN ONE COMMAND FOREVER
$ npm i -g aws-cdk
$ cd infra && cdk init app --language typescript
$ cdk bootstrap aws://<account-id>/us-east-1
$ cdk deploy
What the stack creates. Three DynamoDB tables, three Lambda functions with Function URLs, one least-privilege role per function, an S3 bucket for vector snapshots, and the billing alarm.
Why everything lives in CDK. Under the Free Plan the account can close at six months. If every resource is code, rebuilding in a fresh account is one command rather than an archaeology exercise.
Least privilege per function, not one shared role. registry-fn cannot touch the gaps table; search-fn cannot mutate the registry. The roles are where the invariants become real.

## Slide 20
BUILD · STEP 5
DynamoDB table design
Table | Partition key | Sort key | Also holds
tools | tool_id | version | name, description, mcp_url, category, owner, vector
events | event_id | ts | type, actor (agent + session), payload
gaps | gap_id | ts | query, top_k with scores, reason, threshold T, actor
Version as the sort key is what makes versions immutable. A new version is a new item, not an edit. The old row is physically untouched, so dependents keep resolving to what they were built against.
Store the vector on the tool row. 1024 floats as base64 binary is about 4 KB — far inside the 400 KB item limit, and a cold start then needs one query rather than a join.
Add a day-bucketed index for replay. A GSI keyed on the date makes 'replay every event in order' a query instead of a full scan. Phase 2 scoring depends on that replay staying cheap.

## Slide 21
BUILD · STEP 6
Append-only, enforced by IAM
The invariant is worth nothing if it lives only in application code.
THE EVENTS AND GAPS ROLE — ALLOW PLUS AN EXPLICIT DENY
{ "Effect": "Allow",
"Action": ["dynamodb:PutItem", "dynamodb:Query", "dynamodb:GetItem"],
"Resource": "arn:aws:dynamodb:*:*:table/endless-events" }
{ "Effect": "Deny",
"Action": ["dynamodb:UpdateItem", "dynamodb:DeleteItem", "dynamodb:BatchWriteItem"],
"Resource": "arn:aws:dynamodb:*:*:table/endless-events" }
The explicit Deny is the point. An Allow that merely omits UpdateItem can be widened later by accident. An explicit Deny cannot be overridden by any other policy, so the invariant survives future carelessness.
BatchWriteItem is denied too. It can delete. Denying only DeleteItem leaves the back door open — an easy one to miss.

## Slide 22
BUILD · STEP 7
The three Lambda functions
Function | Memory | Does | Writes to
registry-fn | 512 MB | POST /tools, GET /tools/{id}[/{version}] | tools
search-fn | 1024 MB | POST /search — embed, rank, decide gap | events, gaps
events-fn | 512 MB | internal append-only writer | events
The always-free allowance is generous here. 1M requests and 400,000 GB-seconds a month. At 512 MB that is roughly 800,000 seconds of execution — Phase 0 will not come close.
Cache the vectors in module scope. Load the S3 snapshot once per cold start into a module-level variable; every warm invocation then skips the load. This is what makes brute-force search viable.
Function URLs, not API Gateway. One URL per function, no extra service, no 12-month clock. Use AWS_IAM auth for registry and events; search can stay open during development.
Give search-fn more memory than it needs. Lambda scales CPU with memory, so 1024 MB makes the cosine loop and JSON parsing faster and often costs the same or fewer GB-seconds overall.

## Slide 23
BUILD · STEP 8
The embedding call
ONE CALL, SHARED BY REGISTRY AND SEARCH
const out = await bedrock.send(new InvokeModelCommand({
modelId: "amazon.titan-embed-text-v2:0",
contentType: "application/json",
body: JSON.stringify({
inputText: text, // up to 8192 tokens
dimensions: 1024, // 512 and 256 also supported
normalize: true // lets cosine reduce to a dot product
})
}));
Normalize at the source. With normalized vectors, cosine similarity is just a dot product — less code in the hot path and no chance of normalising inconsistently between indexing and querying.
Embed the same way in both places. Tool descriptions and queries must go through one shared function. Different preprocessing on the two sides is a silent and very common recall killer.
Log token spend on every call. It is the only line item that costs money, so the phase's true cost should be measured, not estimated.

## Slide 24
BUILD · STEP 9
Deploy and verify — the runbook
Each step has an expected result. If one does not match, stop.
# | Action | Expected result
1 | cdk deploy | Three tables, three function URLs, alarm created
2 | Register a tool | Returns tool_id@1
3 | Register the same tool again | Returns @2; the @1 row is byte identical
4 | Search for something seeded | Ranked results, plus one new row in events
5 | Search for nonsense | A gap row with the full top-k and the value of T
6 | Call UpdateItem on events by hand | AccessDenied — this is the invariant test
7 | Check CloudWatch | Token spend logged; the billing alarm stays quiet
Step 6 is the one people skip. An append-only log that has never been attacked is only a claim — run the denial and watch it fail.

## Slide 25
COST
What this actually costs
One correction worth knowing before you write the CDK.
DynamoDB's always-free 25 WCU / 25 RCU applies to PROVISIONED capacity only. On-demand mode is not covered — an on-demand table bills from the first request.
Service | Free allowance | Phase 0 usage | Cost
Lambda | 1M requests + 400k GB-s monthly, always | a few thousand requests | $0
DynamoDB | 25 GB + 25 WCU / 25 RCU provisioned, always | 3 tables at 5/5 = 15/15 | $0
S3 | 5 GB (12-month tier) | a few MB of snapshots | $0
CloudWatch | 5 GB of logs, always | well inside | $0
Bedrock | none — this one is paid | ~20 tools + a few thousand queries | under $2
Total for the phase: under $2. The only ways to overspend are leaving a table in on-demand mode or drifting into a second region.

## Slide 26
PART FOUR
The plan
Twelve issues, one critical path, one gate.

## Slide 27
PLAN
Twelve issues
T-shirt estimates for one developer.
# | Issue | Est. | Depends on
1 | Scaffold repo with the phantom/visual split | S | -
2 | Define shared schemas: tool, event, gap | S | 1
3 | CDK stack: tables, IAM, billing alarm | M | 1
4 | Registry service with immutable versioning | M | 2, 3
5 | Embedding pipeline on Bedrock Titan V2 | M | 3
6 | Semantic search endpoint | M | 4, 5
7 | Append-only event log with provenance | M | 2, 3
8 | Gap detection and gap log | M | 6, 7
9 | Seed 15-20 tools wrapping public APIs | L | 4
10 | Labelled eval set and recall@k harness | L | 6, 9
11 | Query CLI and miss-log review CLI | M | 8, 9
12 | Phase 0 findings write-up | S | 10, 11

## Slide 28
PLAN
Critical path and where to parallelise
#1 Scaffold
#3 CDK
#4 Registry
#6 Search
#10 Eval
#12 Findings
#9 is the big one, and it runs in parallel. Seeding 15-20 tools is the largest single item and depends only on #4. Start it the moment the registry accepts writes.
#2 and #3 both unblock straight after #1. Schemas and infrastructure have no dependency on each other.
#10 cannot start early. The eval harness needs working search (#6) and a seeded registry (#9). It is the last real work and the one that produces the answer.
Nearly half the phase is #9 plus #10. That is correct, not a mis-estimate. Those two decide whether Phase 0 produces evidence.

## Slide 29
THE GATE
Recall@3 of 0.9, or the gap log means nothing
50+ labelled queries. Each written against the seeded set and labelled with the tool that should win.
About 15 with no correct answer. Genuine gaps, known in advance. Without them the harness cannot measure whether real gaps are detected.
Three numbers reported. recall@1, recall@3, and the false-gap rate — gaps logged where a correct tool existed and search simply missed it.
The gate. Until recall@3 reaches 0.9, no gap is treated as evidence. The number goes in the findings either way.
A 50-query set can show that search is badly broken. It cannot prove search is good. Treat 0.9 as a floor for proceeding, never as a claim of quality.

## Slide 30
RISKS
What could make this phase produce noise
Tool descriptions set the ceiling. Twenty carelessly written descriptions produce bad recall and a gap log full of false gaps — the phase will have measured your writing, not the idea.
Threshold T does a lot of quiet work. Too low and nothing logs; too high and everything does. Recording T on each gap keeps old records honest when the value changes.
Region drift. Bedrock in one region and tables in another is the most common way a weekend disappears.
Cold start is not a technical problem. No agents without tools, no tools without agent traffic. Seeding is the mitigation; the gaps board is a product on its own.
The six-month account clock. Under the Free Plan the account closes when credits run out. Everything lives in CDK so a rebuild is one command.

## Slide 31
OPEN
Eight assumptions to confirm or overrule
None of these were specified in PROJECT.md or CLAUDE.md.
Decision | Assumed | Why
Language | TypeScript / Node 20 | CLAUDE.md defines a tool as an MCP server
Compute | Lambda + Function URLs | Always free; skips API Gateway
Store | DynamoDB, provisioned | Always free at 25 GB and 25/25
Vector search | Brute-force cosine | 20 tools needs no database
Embeddings | Bedrock Titan V2 | Native to AWS, costs cents
IaC | AWS CDK (TypeScript) | Same language as the services
Surface | HTTP API + CLI only | Roadmap says read the log by hand
Execution | Out of scope | Keeps the sandbox invariant untriggered

## Slide 32
NEXT
Where this goes from here
1
Confirm or overrule the eight assumptions
2
Confirm the AWS account type — Free Plan or legacy 12-month tier
3
Pick the region and enable Bedrock Titan V2 model access there
4
Create issues #1-#12 in Endlessandothers/Endlessproject
5
Start #1 and #3 in parallel
Plan: docs/plans/phase-0-plan.md · Board: miro.com/app/board/uXjVHpGFCos=