## Slide 1
ENDLESS
Phase 0 — Validate the Loop
The smallest system that can tell a real unsolved need from a search failure. Built on AWS always-free services.
Endlessandothers/Endlessproject · 8 September 2026 · 12 issues · about 6 weeks · under $2

## Slide 2
CONTEXT
What Endless is
A shared universe of small tools that AI agents discover and call.
The inversion. Most tool marketplaces are static directories: you publish and hope. Endless logs every agent search that finds nothing, so normal usage generates demand signal for free. Creators stop guessing what to build and read what agents repeatedly failed to find.
Phantom layer. The machine substrate — registry, semantic search, gap logging, gravity scoring, routing, sandboxed execution. Ranking here is earned through usage and cannot be purchased.
Visual layer. A navigable 3D world where tools render as celestial bodies sized by their real standing. Sponsorship and paid placement live here only, and it never writes ranking back.
Money buys what humans see. Merit decides what agents use. Collapsing the two would destroy the reason an agent can be trusted to pick well.

## Slide 3
PURPOSE
Phase 0 exists to answer one question
Everything in this phase is built to produce evidence for it.
Is a logged gap real evidence of an unsolved need, or just a search failure?
Why it decides everything. The entire pitch of Endless is that gap logs are a usage-verified map of real unsolved problems. If the signal is noisy, creators are handed a roadmap of nothing, and the core value proposition collapses.
PROJECT.md already flags it. Distinguishing 'no tool exists' from 'the agent searched badly' is named as genuinely unsolved. Search quality has to be strong before gap logging means anything.
So the gate is measured, not asserted. Phase 0 refuses to treat any gap as evidence until a labelled eval set shows recall@3 of at least 0.9.

## Slide 4
SCOPE
What is in Phase 0, and what is deliberately not
In scope | Out of scope — and why
Tool registry with immutable versions | Sandboxed execution — Phase 0 never runs a tool
Semantic search over registered tools | Gravity scoring, mass and brightness — Phase 2
Append-only, provenance-tagged event log | Mini LLMs, heartbeats, routing — Phase 3
Gap detection and gap log | The 3D visual layer — Phase 4
15-20 seeded tools wrapping public APIs | Billing, payouts, sponsorship — Phase 6
Labelled eval set and recall@k harness | Any user interface — CLI only for now
The scope risk is real. PROJECT.md names it: the full vision is five products at once — a registry, a routing system, a 3D world, a sandbox platform and a two-sided economy. Building all of it before anyone uses it is the most likely way this fails. Phases 0-2 need no 3D and no LLM routing, which is why this plan stops hard at the edge of Phase 0.

## Slide 5
ARCHITECTURE
AWS free-tier architecture
Every box below sits inside an always-free monthly limit, except the teal one.
IN
Agent / CLI
the caller
COMPUTE — LAMBDA FUNCTION URLS
Ln
registry-fn
tool CRUD, immutable versions
Ln
search-fn
embed, cosine rank, gap check
Ln
events-fn
append-only writer
STORAGE — DYNAMODB (25 GB FREE)
DB
tools
PK tool_id / SK version
DB
events
append-only, provenance
DB
gaps
append-only, provenance
ML
Bedrock
Titan Embeddings V2
ONLY PAID COMPONENT
S3
S3
vector snapshots, warm start
CW
CloudWatch
logs and the $5 billing alarm

## Slide 6
WALKTHROUGH
The request path, step by step
1. Caller asks. An agent or the CLI posts a natural-language query to the search-fn Lambda Function URL.
2. Query is embedded. search-fn calls Bedrock Titan Embeddings V2 and gets back a vector. This is the only network call that costs money.
3. Ranking happens in memory. Tool vectors were loaded once at cold start and cached in module scope. Cosine similarity over ~20 vectors is sub-millisecond.
4. An event is written, always. Success or failure, search-fn emits an event carrying the agent id and session id before it returns. Scoring in later phases is recomputed from this log, so it must be complete now.
5. A gap is logged, conditionally. If the top score falls below threshold T, or the caller explicitly rejects every result, a gap record is appended — storing the full top-k with scores and the value of T that was in force.
6. A human reads the log. The phase ends with you reading gaps by hand and judging each one. That is the deliverable: evidence, not infrastructure.

## Slide 7
DESIGN
How the architecture enforces the invariants
CLAUDE.md lists five non-negotiables. Three are live in Phase 0.
Invariant | How Phase 0 enforces it
Gap logs are append-only and provenance-tagged | IAM grants PutItem and Query but not UpdateItem or DeleteItem
Tool versions are immutable once published | Re-registering writes a new SK version; a test proves no mutation
Scoring recomputable from the event log | Every search emits an event; a test replays the log to recompute
All third-party code runs sandboxed | Not yet triggered — Phase 0 never executes a registered tool
Money never affects agent-facing ranking | Not yet triggered — no money, no ranking, no visual layer
The last two are scope decisions, not oversights. The moment execution arrives in Phase 1, mandatory sandboxing gates everything — it is the invariant that must be built before the first untrusted tool runs.

## Slide 8
KEY DECISION
The deliberate non-decision: no vector database
Phase 0 has 15-20 tools. Cosine similarity over 20 vectors held in Lambda memory is sub-millisecond and costs nothing at all.
A vector store would answer none of the phase's questions. Standing up OpenSearch or pgvector for 20 rows spends the phase on infrastructure instead of evidence — and OpenSearch is not always-free.
The interface is what matters. Search sits behind an interface with a single implementation, so the store can be swapped in Phase 1 without touching a single caller.
Choose it later, with data. The Phase 1 vector store gets picked using real query distributions from Phase 0, rather than guessed at now.
The same reasoning picked Lambda Function URLs over API Gateway: Lambda and DynamoDB are always free, API Gateway is free for 12 months only. Given the free-tier change, that distinction matters.

## Slide 9
COST
AWS changed the free tier — the plan is built around it
 | Legacy free tier | Free Plan (since 9 July 2025)
Who gets it | Accounts opened before 9 Jul 2025 | All new accounts
Shape | 12 months of per-service limits | $100 credit, up to $200, over 6 months
What happens at the end | Tier expires, billing continues | The account itself closes
Always-free services | Unaffected | Unaffected
The design response. Lean on always-free limits — Lambda (1M requests and 400k GB-seconds per month) and DynamoDB (25 GB) — so the plan works under either account type.
Total cost for the phase: under $2. Embeddings for 20 tool descriptions plus a few thousand queries is well under a million tokens at roughly $0.02 per million.
Set the $5 billing alarm on day one. It is issue #3, not an afterthought. A 6-week phase inside a 6-month clock is comfortable — but do not let it drift.

## Slide 10
PLAN
Twelve issues
T-shirt estimates for one developer.
# | Issue | Est. | Depends on
1 | Scaffold repo with the phantom/visual split | S | -
2 | Define shared schemas: tool, event, gap | S | 1
3 | CDK stack: tables, IAM, billing alarm | M | 1
4 | Registry service with immutable versioning | M | 2, 3
5 | Embedding pipeline on Bedrock Titan V2 | M | 3
6 | Semantic search endpoint | M | 4, 5
7 | Append-only event log with provenance | M | 2, 3
8 | Gap detection and gap log | M | 6, 7
9 | Seed 15-20 tools wrapping public APIs | L | 4
10 | Labelled eval set and recall@k harness | L | 6, 9
11 | Query CLI and miss-log review CLI | M | 8, 9
12 | Phase 0 findings write-up | S | 10, 11

## Slide 11
SEQUENCING
Critical path and where to parallelise
#1 Scaffold
#3 CDK
#4 Registry
#6 Search
#10 Eval
#12 Findings
#9 is the big one, and it runs in parallel. Seeding 15-20 tools is the largest single item, and it depends only on #4. Start it the moment the registry accepts writes and run it alongside #5 through #8.
#2 and #3 both unblock straight after #1. Schemas and infrastructure have no dependency on each other.
#10 cannot start early. The eval harness needs both working search (#6) and a seeded registry (#9). It is the last real work of the phase and the one that produces the answer.
Nearly half the phase is #9 plus #10. That is correct, not a mis-estimate. Those two decide whether Phase 0 produces evidence or noise.

## Slide 12
THE GATE
Recall@3 of 0.9, or the gap log means nothing
50+ labelled queries. Each written against the seeded set and labelled with the tool that should win.
About 15 with no correct answer. Genuine gaps, known in advance. Without these the harness cannot measure whether real gaps are detected.
Three numbers reported. recall@1, recall@3, and the false-gap rate — gaps logged where a correct tool existed and search simply missed it.
The gate. Until recall@3 reaches 0.9, no gap is treated as evidence of anything. The number is recorded in the findings either way.
A 50-query set can show that search is badly broken. It cannot prove search is good. Treat 0.9 as a floor for proceeding, never as a claim of quality.

## Slide 13
RISKS
What could make this phase produce noise
Tool descriptions set the ceiling. Twenty carelessly written descriptions produce bad recall and a gap log full of false gaps — and the phase will have measured your writing, not the idea.
Threshold T does a lot of quiet work. Too low and nothing logs; too high and everything does. Recording T on each gap record keeps old gaps honest when the value changes.
Bedrock region availability. Titan Text Embeddings V2 is not in every region. Confirm it before issue #5 or the pipeline stalls.
Cold start is not a technical problem. Two-sided marketplace: no agents without tools, no tools without agent traffic. Seeding is the mitigation, and the gaps board is a product on its own.
The 6-month account clock. Under the Free Plan the account closes when credits run out. Everything lives in CDK so a rebuild in a fresh account is one command.

## Slide 14
OPEN
Eight assumptions to confirm or overrule
None of these were specified in PROJECT.md or CLAUDE.md.
Decision | Assumed | Why
Language | TypeScript / Node 20 | CLAUDE.md defines a tool as an MCP server
Compute | Lambda + Function URLs | Always free; skips API Gateway
Store | DynamoDB | Always free at 25 GB
Vector search | Brute-force cosine | 20 tools does not need a database
Embeddings | Bedrock Titan V2 | Native to AWS, costs cents
IaC | AWS CDK (TypeScript) | Same language as the services
Surface | HTTP API + CLI only | The roadmap says read the log by hand
Execution | Out of scope | Keeps the sandbox invariant untriggered

## Slide 15
NEXT
Where this goes from here
1
Confirm or overrule the eight assumptions
2
Confirm the AWS account type — pre- or post-July-2025 free tier
3
Confirm Bedrock Titan V2 is available in your chosen region
4
Create issues #1-#12 in Endlessandothers/Endlessproject
5
Start #1 and #3 in parallel
Plan: docs/plans/phase-0-plan.md · Board: miro.com/app/board/uXjVHpGFCos=